## Rajneet Kaur Deol
Project Task List
TASK | PRIORITY | STATUS | Estimated START DATE | Estimated DUE DATE | Actual Start Date | Hours | % COMPLETE | DONE? | Actual Completion Date | NOTES
Conduct competitor analysis | Normal | Complete | 2024-05-21 | 2024-05-28 | 2024-05-22 | 4 | 100% | 1 | 2024-05-22
Research for website names | Low | Complete | 2024-05-28 | 2024-05-28 | 2024-05-28 | 5 | 100% | 1 | 2024-05-28
Research for website designs | Low | Complete | 2024-06-02 | 2024-06-08 | 2024-06-04 | 3 | 100% | 1 | 2024-06-07
research Using differnet platforms to design a website (wix) | Normal | Complete | 2024-06-11 | 2024-06-14 | 2024-06-11 | 5 | 100% | 1 | 2024-06-14
Write info for the webpage. (homepage, index) | Normal | Complete | 2024-05-30 | 2024-06-05 | 2024-05-30 | 4.5 | 100% | 1 | 2024-06-05
design the website logo and the slogan | Normal | Complete | 2024-06-12 | 2024-06-12 | 2024-06-12 | 4 | 100% | 1 | 2024-06-12
write the code for the website which is just basic display with website logo and slogan on it | High | Complete | 2024-06-02 | 2024-06-20 | 2024-06-07 | 7 | 100% | 1 | 2024-06-20
Make the privacy policies for the website | Normal | Complete | 2024-06-19 | 2024-06-19 | 2024-06-19 | 5 | 100% | 1 | 2024-06-19
Compile design ideas and present to the team | High | Complete | 2024-08-04 | 2024-08-24 | 2024-06-21 | 1.5 | 100% | 1 | 2024-07-02
will make the website buying plans in it for the services | Normal | Complete | 2024-06-23 | 2024-06-26 | 2024-06-27 | 6 | 100% | 1 | 2024-06-29
add the buying plans to the design code webpage | Normal | Complete | 2024-06-30 | 2024-07-05 | 2024-07-01 | 4.5 | 100% | 1 | 2024-07-05
finish the whole design code for the website | High | Complete | 2024-06-24 | 2024-07-13 | 2024-06-26 | 4.5 | 100% | 1 | 2024-07-31
will add the privacy policies to the website | Normal | Complete | 6/30/204 | 2024-07-05 | 2024-07-02 | 2.5 | 100% | 1 | 2024-07-05
the html coding of the signup and loginup | Normal | Complete | 2024-07-01 | 2024-07-06 | 2024-07-01 | 3 | 100% | 1 | 2024-07-07
add more design and innovative images and ideas for the index (homepage) | High | Complete | 2024-07-03 | 2024-07-14 | 2024-07-06 | 4 | 100% | 1 | 2024-07-31
do the modficications in styles.css where it is required after writing the code | Normal | Complete | 2024-07-04 | 2024-07-08 | 2024-07-05 | 4.25 | 100% | 1 | 2024-07-10
test the code i found for login and signup to work for the website | High | Complete | 2024-07-09 | 2024-07-13 | 2024-07-09 | 2 | 100% | 1 | 2024-07-09
Design and implement code using Azure WordPress. | Low | Complete | 2024-07-23 | 2024-07-27 | 2024-07-24 | 2 | 100% | 1 | 2024-07-25
Configure the 'Contact Us' form to send submissions directly to syncshare6@outlook.com. | High | Complete | 2024-07-25 | 2024-08-06 | 2024-07-26 | 3 | 100% | 1 | 2024-08-04
Develop and finalize content describing SyncShare’s secure file sharing platform. | Low | Complete | 2024-07-29 | 2024-07-29 | 2024-07-29 | 1 | 100% | 1 | 2024-07-29
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Formulas:
Estimated DUE DATE = ToDoList2[[#This Row],[Estimated START DATE ]]+7

## Deergha.
Project Task List
TASK | PRIORITY | STATUS | Estimated START DATE | Estimated DUE DATE | Estimated hours | Actual Start Date | Hours | % COMPLETE | DONE? | Actual Completion Date | NOTES
Register Domain: Choose a registrar, create an account, and register the domain. | Normal | Complete | 2024-05-20 | 2024-05-25 | 4 | 2024-05-21 | 5 | 100% | 1 | 2024-05-26 | Domain registration included researching registrars, creating an account, and completing the registration.
Choose Hosting Platform: Research hosting types, performance, support, features, and pricing | High | Complete | 2024-06-03 | 2024-06-10 | 5 | 2024-06-10 | 3 | 100% | 1 | 2024-06-11 | Hosting platform research focused on comparing types, performance, support, features, and pricing.
Plan Website: Define purpose, target audience, goals, and create a site map. | Normal | Complete | 2024-05-27 | 2024-06-11 | 3 | 2024-05-28 | 10 | 100% | 1 | 2024-06-10 | Planning phase included defining the website's purpose, target audience, goals, and creating a site map.
Design Layout: Develop wireframes and mockups ensuring a responsive design. | Normal | Complete | 2024-06-07 | 2024-06-15 | 3.5 | 2024-06-08 | 15 | 100% | 1 | 2024-06-13 | Design phase involved creating wireframes and mockups with a focus on responsive design.
Set Up GitHub Repository: Create and clone a repository locally. | High | Complete | 2024-06-12 | 2024-06-15 | 3 | 2024-06-12 | 2 | 100% | 1 | 2024-06-14 | GitHub repository was set up and cloned locally for version control and collaboration.
Develop Website: Code using HTML, CSS, and JavaScript. | High | Complete | 2024-06-13 | 2024-06-18 | 5 | 2024-06-13 | 40 | 100% | 1 | 2024-06-18 | Development involved coding the website using HTML, CSS, and JavaScript, based on the planned design.
Commit and Push Changes: Regularly update the repository on GitHub. | Normal | Complete | 2024-06-15 | 2024-06-17 | 4 | 2024-06-15 | 20 | 100% | 1 | 2024-06-18 | Regular commits and updates were made to the GitHub repository to keep the codebase current.
Test Website: Ensure functionality across different browsers and devices. | High | Complete | 2024-06-17 | 2024-06-19 | 5 | 2024-06-18 | 16 | 100% | 1 | 2024-06-19 | Testing phase included checking website functionality across various browsers and devices for compatibility.
Deploy and Maintain: Deploy the site and continuously update content and fix issues. | Normal | Complete | 2024-06-19 | 2024-06-20 | 6 | 2024-06-19 | 5 | 100% | 1 | 2024-06-21 | Deployment phase involved launching the site, with initial updates and fixes ongoing to ensure smooth operation.
Setup and Configuration: Initialize Node.js project, install packages | Normal | Complete | 2024-06-20 | 2024-06-30 | 5 | 2024-06-22 |  | 100% | 1 | 2024-06-30 | The initial setup phase included creating a new Node.js project and installing all necessary packages. This provided the foundation for the project.
Server Setup: Create Express server, setup middleware | Low | Complete | 2024-06-26 | 2024-06-30 | 5 | 2024-06-28 |  | 100% | 1 | 2024-07-01 | Created the Express server and set up essential middleware for handling requests, responses, and errors.
Routing and Controllers: Define routes, implement controllers | Normal | Complete | 2024-06-28 | 2024-07-03 | 5 | 2024-06-28 |  | 100% | 1 | 2024-07-04 | Defined the application routes and implemented the controllers to handle various endpoints.
File Upload Handling: Setup, multer , create upload endpoints | High | Complete | 2024-07-01 | 2024-07-04 | 4 | 2024-07-02 |  | 100% | 1 | 2024-07-03 | Implemented file upload functionality using Multer and created endpoints for handling file uploads.
File Storage and Management: Decide storage strategy, implement storage logic | Normal | Complete | 2024-07-05 | 2024-07-10 | 5 | 2024-07-03 |  | 100% | 1 | 2024-07-10 | Chose the appropriate storage strategy for uploaded files and implemented the logic for storing and retrieving files.
Database Integration: Set up database connection, create schema/models | Low | Complete | 2024-07-12 | 2024-07-15 | 3 | 2024-07-10 |  | 100% | 1 | 2024-08-06 | Established the database connection and created the necessary schema and models for managing data.
Error Handling and Validation: Implement error handling, add validation | Low | Complete | 2024-07-10 | 2024-07-16 | 2 | 2024-07-10 |  | 100% | 1 | 2024-08-06 | Added robust error handling mechanisms and input validation to ensure the application is secure and handles edge cases properly.
Finalize User Authentication : Complete the implementation of user login and registration functionality. | High | Complete | 2024-07-12 | 2024-07-23 | 6 | 2024-07-16 |  | 100% |  | 2024-08-06 | Ensure secure password storage using hashing, and validate user inputs to prevent SQL injection.
Set Up File Management Interface: Create a user interface for managing uploaded files (view, delete, rename). | Normal | Complete | 2024-07-23 | 2024-08-05 | 5 | 2024-07-25 |  | 100% | 1 | 2024-08-06 | Make the interface intuitive and ensure it communicates effectively with the backend.
Enhance Download Functionality: Improve the user interface for downloading files and ensure it works seamlessly. | Normal | Complete | 2024-08-25 | 2024-08-04 | 4 | 2024-07-20 |  | 100% | 1 | 2024-08-06 | Optimize the download process for different file types and sizes.
Integrate MySQL Database with User Data: Connect the PHP backend to MySQL for storing and retrieving user data. | High | Complete | 2024-08-24 | 2024-08-06 | 3 | 2024-07-21 |  | 100% | 1 | 2024-08-06 | Ensure efficient queries and handle database connections securely.
Conduct Security Audit: Perform a thorough security audit on the entire website | High | Complete | 2024-08-28 | 2024-08-04 | 4 | 2024-07-22 |  | 100% | 1 | 2024-08-06 | Look for common vulnerabilities like XSS, CSRF, and SQL injection.
Test the Complete System: Perform extensive testing of all functionalities, including edge cases. | Normal | Complete | 2024-08-29 | 2024-08-05 | 5 | 2024-07-30 |  | 100% | 1 | 2024-08-06 | Write and execute test cases, fix any bugs discovered during testing.
Review and Refactoring: Conduct code review and refactor for improved performance. | Normal | Complete | 2024-08-30 | 2024-08-05 | 6 | 2024-07-31 |  | 100% | 1 | 2024-08-06 | Conducted a thorough code review and refactoring to enhance performance, readability, and maintainability of the codebase. This step ensured the application runs efficiently and is easier to maintain and scale in the future.
Formulas:
Estimated DUE DATE = ToDoList26[[#This Row],[Estimated START DATE ]]+5

## Rebecca White
Project Task List
TASK | PRIORITY | STATUS | Estimated START DATE | Estimated DUE DATE | Estimated Hours | Actual Start Date | Hours | % COMPLETE | DONE? | Actual Completion Date | NOTES
Set up billing and subscription on Azure | High | Complete | 2024-06-11 | 2024-06-11 | 2 | 2024-06-11 | 2 | 100% | 1 | 2024-06-11 | Monitor usage and costs regularly to avoid unexpected charges
Create an Azure account | High | Complete | 2024-06-11 | 2024-06-11 | 0.5 | 2024-06-11 | 0.5 | 100% | 1 | 2024-06-11 | Verified account details and ensured accurate billing information. Shared credentials securely with team.
Create an Azure resource group to logically group related Azure resources | Low | In Progress | 2024-06-27 | 2024-06-30 | 0.25 | 2024-08-01 | 1 | 100% | 1 | 2024-08-01 | Maintain consistency and clarity across the project by organizing resources effectively.
Set up Azure storage account | Normal | In Progress | 2024-06-27 | 2024-06-30 | 0.25 | 2024-08-01 | 1 | 100% | 1 | 2024-08-01 | Consider redundancy and scalability requirements. Review access tiers and lifecycle management policies for cost optimization.
Research Azure Blob Storage | Low | Complete | 2024-06-18 | 2024-06-20 | 0.5 | 2024-06-17 | 0.5 | 100% | 1 | 2024-06-18 | Explored best use cases for Azure Blob Storage relevant to our website needs.
Research Azure File Storage options | Low | Complete | 2021-06-17 | 2024-06-20 | 1 | 2021-06-17 | 1 | 100% | 1 | 2021-06-18 | Explore Azure's file storage services and their suitability for our project's file sharing needs.
Research Cloud Services for pricing | High | Complete | 2024-06-19 | 2024-06-25 | 1 | 2024-06-19 | 1 | 100% | 1 | 2024-07-28 | 1. https://www.terabox.com/cloud-storage-pricing-plans ($3.29/month)
Evaluate Azure Storage pricing models | High | Complete | 2021-06-17 | 2024-06-20 | 1 | 2021-06-17 | 1 | 100% | 1 | 2021-06-18 | Compare pricing structures for Azure storage solutions to optimize cost-efficiency.
Configure storage access controls and permissions | Low | Not Started | 2024-06-27 | 2024-06-30 | 0.25 | 2021-06-17 | 0.25 | 100% | 1 | 2024-08-01 | Define and implement access policies to secure data stored in Azure Blob Storage.
Evaluate Azure Backup and Restore Solutions | Normal | Complete | 2021-06-17 | 2024-06-20 | 0.5 | 2021-06-17 | 0.5 | 100% | 1 | 2021-06-17 | Investigate Azure Backup solutions for data protection and disaster recovery, ensuring critical files and configurations are backed up and recoverable.
Study Azure Monitoring and Alerts | Low | Complete | 2021-06-17 | 2024-06-20 | 0.5 | 2021-06-17 | 0.5 | 100% | 1 | 2021-06-17 | Explore Azure Monitor and Application Insights for real-time monitoring, logging, and performance insights to proactively manage and troubleshoot the file sharing platform.
Research Azure Web Apps | High | Complete | 2024-06-16 | 2024-06-21 | 1 | 2024-06-16 | 1 | 100% | 1 | 2024-06-16 | Explored Azure Web Apps for hosting and managing web applications, including pricing, scalability, and deployment options. Determined that the cost is too high for our current project needs.
Participate in sprint planning 2 | High | Complete | 2024-06-24 | 2024-07-20 | 1 | 2024-07-09 | 1 | 100% | 1 | 2024-07-16 | Collaborate on defining sprint goals and tasks.
Cloned the team’s public repository to the local computer. | Normal | Complete | 2024-07-12 | 2024-07-20 | 1 | 2024-07-12 | 1.5 | 100% |  | 2024-07-12 | Cloned sucessfully to local computer.
Identify risks associated with Azure storage solutions and implement mitigation strategies | Low | In Progress | 2024-06-24 | 2024-07-20 | 1 | 2024-07-18 |  | 100% | 1 | 2024-07-18 | Address potential issues in Azure storage implementation.
Resolved issues with email notifications and improved email templates | Low | Complete | 2024-08-06 | 2024-08-06 | 1 | 2024-08-06 | 1 | 100% |  | 2024-08-06 | Ensuring email notifications are sent correctly and templates are visually appealing.
Researched user authorization on Windows | High | Complete | 2024-07-13 | 2024-07-20 | 1 | 2024-07-13 | 1 | 100% |  | 2024-07-13 | Found Auth0 for login, sign-up.
Participate in making the website code | High | In Progress | 2024-06-24 | 2024-07-20 | 8 | 2024-07-12 | 12 | 50% | 0 |  | Contribute to the development of website functionality.
Ensure documentation is up-to-date | High | Complete | 2024-06-24 | 2024-07-20 | 2 | 2024-07-16 | 1 | 100% | 1 | 2024-07-16 | Keep project documentation current and accessible.
Installed Flask and other necessary dependencies. | Low | Complete | 2024-07-12 | 2024-07-20 | 1 | 2024-07-12 | 1 | 100% |  | 2024-07-12 | Successfully done.
Configured file sharing locally | High | Complete | 2024-07-19 | 2024-07-21 | 4 | 2024-07-19 | 2.5 | 100% |  | 2024-07-21 | Successfully done locally.
Attend sprint review sessions to demonstrate completed work and gather feedback | High | Complete | 2024-06-24 | 2024-07-20 | 1 | 2024-07-16 | 2 | 100% | 1 | 2024-07-16 | Attend sprint review sessions to show what's done and get suggestions for improvements
Participate in sprint planning 3 | High | In Progress | 2024-07-22 |  | 2 | 2024-07-20 | 2 |  | 0

## Sam Liang
Project Task List
TASK | PRIORITY | STATUS | Estimated START DATE | Estimated DUE DATE | Estimated Hours | Actual Start Date | Hours | % COMPLETE | DONE? | Actual Completion Date | NOTES
Meet team on May28 and started the project plan | Normal | Complete | 2024-06-03 | 2024-06-10 | 3 | 2024-05-28 | 1 | 100% | 1
Research and practice storage account in Azure | Normal | Complete | 2024-06-03 | 2024-06-07 | 3 | 2024-06-15 | 3 | 100% | 1 |  | 2
Research file sharing platiform in Azure | Normal | Complete | 2024-06-04 | june 22 2024 | 2 | 2024-06-11 | 2 | 100% | 1
Research how github and azure communicate from Github documentation | Normal | In Progress | 2024-06-05 | 2024-06-05 | 2.5 | 2024-06-11 | 1.5 | 100% | 1
Build Azure Subscription and Users | High | Complete | 2024-06-06 | 2024-06-10 | 2.5 | 2024-06-11 | 2 | 100% | 1
Once 6&7 finished, figure out the best way they communicate to each other. | Normal | In Progress | 2024-06-07 | 2024-06-20 | 2 | 2024-06-12 | 2 | 100% | 1
Assist emplementing the communication medth with website design. | High | In Progress | 2024-06-08 | 2024-06-22 | 2 | 2024-06-12 | 2 | 100% | 1
Finallize the project plan with team | High | In Progress | 2024-06-09 | 2024-06-22 | 2 | 2024-06-12 | 2 | 100% | 1
Prepare presentation with team | Normal | Not Started | 2024-06-10 | 2024-06-20 | 2 | 2024-06-19 | 2 | 100% | 1
Research and figure out options for users authentication for File Sharing account access | Normal | Complete | 2024-06-30 | 2024-07-03 | 2 | 2024-07-03 |  | 100% | 1
Installing GitHub and related packages in local Linux VM | Normal | Complete | 2024-07-04 | 2024-07-05 | 2 | 2024-07-05 |  | 100% | 1
Installing and MYSQL and Script related packages inside local Linux VM | Normal | Complete | 2024-07-09 | 2024-07-09 | 2 | 2024-07-09 |  | 100% | 1
Work on MYSQL database in local Linux VM to store users account info | Normal | Complete | 2024-07-10 | 2024-0711 | 2 | 2024-07-10 |  | 100% | 1
Figure out how to make MYSQL database | Normal | Complete | 2024-07-06 | 2024-07-16 | 4 | 2024-07-06 |  | 100% | 1
Finishing spring2 report, updating task lists and business canvas | High | In Progress | 2024-07-12 | 2024-07-15 | 4 | 2024-07-15 |  | 100% | 1
Create local storage path in Linux and Testing upload function locally | Normal | Complete | 2024-07-20 | 2024-07-20 | 4 | 2024-07-20 |  | 100% | 1
| High | In Progress | 2024-07-23 | 2024-08-02 | 4.5 |  |  |  | 0
Reseach and figuring out how to implemt the upload function cross internet with team | [8 empty] | 0
Formulas:
Estimated DUE DATE = ToDoList27[[#This Row],[Estimated START DATE ]]+7
Estimated DUE DATE = ToDoList27[[#This Row],[Estimated START DATE ]]